## Sheet1
Priority? | RMA? | CPQ Order | concate cpq + vesion | Initial Version Created Date | Latest Version Created Date / Modified Date | Order Submitted Date | Added to ESS Hold Date | Version Hold Status | Reporting Status | IN ESS Hold Queue | Old Order Status | update? | CPQ Status | Most Recent Order Version/ Version in ESS Approval | Is SIF available? | SIF Order File name/s (from CPQ Production) // EDI Purchase Order | Total # of lines | # of SPECIALS lines | In SIF Folder | CPQ Test order # // CPQ Prod Order | Substitute CPQ Test order # | Overall Order Status | AST: WD Code Changes Migrated to ERP Prod? | AST: Code Changes Migrated to CPQ Prod? | Ready to Release/ Submit Order? | SIF File Status: Syteline | Syteline Test notes | SIF File Status: Oracle CPQ | Oracle CPQ Test Notes | SIF File Status: Oracle ERP | Oracle ERP Test Notes | ESS BOM Validation Status | BOM Test Notes What is the error/issue on BOM/Routing? | Next Action **Enter most recent comment on top line in cell** Start With: Initials Date Time (in EST) | Next Action With | JIRA | Resolved? | Resolution | Resolved Date | In ERP Prod Validation Process? Y/N | Date Released to ERP Prod | Date ERP Hold Released | Initials of ESS who Released Hold | Hold Release Comments | week # of when order was submitted by customer | Date released from ESS hold | # of days for BOM Val | Status Comment
|  | C0005114 | [12 empty] | yes | New Bridge Learning School-DRAWING-RevB-72623.txt | 9 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0005097 | [12 empty] | yes | OPD-013490_r2.txt | 5 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0004384 | [12 empty] | Yes | OE Q-115-MG23M CHOICES (1) 1ST FLR SURPLUS WORKSTATIONS.txt | 20 | 0 |  | DEV7-CPQ-8259 |  | Not Started | [5 empty] | Fail | DEV7-CPQ-8259-Failed to import the item CCTW66B . Error - Configuration is incomplete. Please make further changes and try again.Failed to import the item RTWS2460.GY . Error - Configuration is incomplete. Please make further changes and try again.Failed to import the item H20 . Error - Configuration is incomplete. Please make further changes and try again.Failed to import the item SISTC60 . Error - Configuration is incomplete. Please make further changes and try again.Failed to import the item SISSR66 . Error - Configuration is incomplete. Please make further changes and try again.Failed to import the item SICEERBC . Error - Configuration is incomplete. Please make further changes and try again.
|  | C0004635 | [12 empty] | no | 219652 Trendway SIF U_of_MN_Journalism_110B_teardrop_table_SPEC_219652_05.07.2023.txt | 6 | 0 |  |  |  | Not Started
|  | C0004387 | [12 empty] | no | retina fix.txt | 20 | 0 |  |  |  | Not Started
|  | C0004638 | [12 empty] | no | OPP-005739 specials R1.txt | 6 | 0 |  |  |  | Not Started