## Sheet1
Priority? | RMA? | CPQ Order | concate cpq + vesion | Initial Version Created Date | Latest Version Created Date / Modified Date | Order Submitted Date | Added to ESS Hold Date | Version Hold Status | Reporting Status | IN ESS Hold Queue | Old Order Status | update? | CPQ Status | Most Recent Order Version/ Version in ESS Approval | Is SIF available? | SIF Order File name/s (from CPQ Production) // EDI Purchase Order | Total # of lines | # of SPECIALS lines | In SIF Folder | CPQ Test order # // CPQ Prod Order | Substitute CPQ Test order # | Overall Order Status | AST: WD Code Changes Migrated to ERP Prod? | AST: Code Changes Migrated to CPQ Prod? | Ready to Release/ Submit Order? | SIF File Status: Syteline | Syteline Test notes | SIF File Status: Oracle CPQ | Oracle CPQ Test Notes | SIF File Status: Oracle ERP | Oracle ERP Test Notes | ESS BOM Validation Status | BOM Test Notes What is the error/issue on BOM/Routing? | Next Action **Enter most recent comment on top line in cell** Start With: Initials Date Time (in EST) | Next Action With | JIRA | Resolved? | Resolution | Resolved Date | In ERP Prod Validation Process? Y/N | Date Released to ERP Prod | Date ERP Hold Released | Initials of ESS who Released Hold | Hold Release Comments | week # of when order was submitted by customer | Date released from ESS hold | # of days for BOM Val | Status Comment
|  | C0005087 | [12 empty] | yes | SS 124 inch panel add.txt | 2 | 0 |  |  |  | Not Started | [22 empty] | 1 |  |  | Success
|  | C0005088 | [12 empty] | yes | C0000962 RMA.txt | 1 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0005077 | [12 empty] | yes | txt_OPP-013337 r1-1.txt | 25 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0005103 | [12 empty] | yes | SP-255-TM23M CMS INFO SYSTEMS_AREA A.txt | 54 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0005047 | [12 empty] | yes | C0000507 RMA.txt | 3 | 2 |  |  |  | Not Started | [25 empty] | Success
|  | C0005109 | [12 empty] | yes | OPP-012899 GTM IDC REV1 Furniture OE.txt | 12 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0005114 | [12 empty] | yes | New Bridge Learning School-DRAWING-RevB-72623.txt | 9 | 0 |  |  |  | Not Started | [25 empty] | Success