## Sheet1
Priority? | RMA? | CPQ Order | concate cpq + vesion | Initial Version Created Date | Latest Version Created Date / Modified Date | Order Submitted Date | Added to ESS Hold Date | Version Hold Status | Reporting Status | IN ESS Hold Queue | Old Order Status | update? | CPQ Status | Most Recent Order Version/ Version in ESS Approval | Is SIF available? | SIF Order File name/s (from CPQ Production) // EDI Purchase Order | Total # of lines | # of SPECIALS lines | In SIF Folder | CPQ Test order # // CPQ Prod Order | Substitute CPQ Test order # | Overall Order Status | AST: WD Code Changes Migrated to ERP Prod? | AST: Code Changes Migrated to CPQ Prod? | Ready to Release/ Submit Order? | SIF File Status: Syteline | Syteline Test notes | SIF File Status: Oracle CPQ | Oracle CPQ Test Notes | SIF File Status: Oracle ERP | Oracle ERP Test Notes | ESS BOM Validation Status | BOM Test Notes What is the error/issue on BOM/Routing? | Next Action **Enter most recent comment on top line in cell** Start With: Initials Date Time (in EST) | Next Action With | JIRA | Resolved? | Resolution | Resolved Date | In ERP Prod Validation Process? Y/N | Date Released to ERP Prod | Date ERP Hold Released | Initials of ESS who Released Hold | Hold Release Comments | week # of when order was submitted by customer | Date released from ESS hold | # of days for BOM Val | Status Comment
|  | C0005241 | [12 empty] | yes | OPP-012958 R1.txt | 14 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0005328 | [12 empty] | yes | OPD-014164-R1.txt | 14 | 0 |  |  |  | Not Started
|  | C0002600 | [12 empty] | yes | 20230315 - DPW SUPERVISOR - AUDIT R1 TRENDWAY ONLY.txt,WAITING AREA R1 audit trendway only.txt | 62 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0002670 | [12 empty] | yes | OPP-006510 R2-new.txt | 31 | 2 |  |  |  | Not Started | [25 empty] | Success
|  | C0002947 | [12 empty] | yes | OPP-006045-5A-rev6.txt,OPP-006045-6B-rev5.txt | 20 | 0 |  |  |  | Not Started
|  | C0002617 | [12 empty] | yes | OPP-006590 Shell FCU_ORDER TXT_060523.txt | 44 | 0 |  |  |  | Not Started
|  | C0002593 | [12 empty] | yes | OPP-006874.txt | 11 | 0 |  |  |  | Not Started
|  | C0003459 | [12 empty] | yes | C0003459.sif | 13 | 0 |  |  |  | Not Started
|  | C0003319 | [12 empty] | yes | TRW_NEWAYGO CO_DEBS OFFICE 6-14-23.txt | 4 | 0 |  |  |  | Not Started
|  | C0003867 | [12 empty] | yes | TWY Manitou.txt | 30 | 0 |  |  |  | Not Started
|  | C0005271 | [12 empty] | yes | OPP-013757-08222023-QUOTE TXT.txt | 40 | 0 |  |  |  | Not Started