## Sheet1
Priority? | RMA? | CPQ Order | concate cpq + vesion | Initial Version Created Date | Latest Version Created Date / Modified Date | Order Submitted Date | Added to ESS Hold Date | Version Hold Status | Reporting Status | IN ESS Hold Queue | Old Order Status | update? | CPQ Status | Most Recent Order Version/ Version in ESS Approval | Is SIF available? | SIF Order File name/s (from CPQ Production) // EDI Purchase Order | Total # of lines | # of SPECIALS lines | In SIF Folder | CPQ Test order # // CPQ Prod Order | Substitute CPQ Test order # | Overall Order Status | AST: WD Code Changes Migrated to ERP Prod? | AST: Code Changes Migrated to CPQ Prod? | Ready to Release/ Submit Order? | SIF File Status: Syteline | Syteline Test notes | SIF File Status: Oracle CPQ | Oracle CPQ Test Notes | SIF File Status: Oracle ERP | Oracle ERP Test Notes | ESS BOM Validation Status | BOM Test Notes What is the error/issue on BOM/Routing? | Next Action **Enter most recent comment on top line in cell** Start With: Initials Date Time (in EST) | Next Action With | JIRA | Resolved? | Resolution | Resolved Date | In ERP Prod Validation Process? Y/N | Date Released to ERP Prod | Date ERP Hold Released | Initials of ESS who Released Hold | Hold Release Comments | week # of when order was submitted by customer | Date released from ESS hold | # of days for BOM Val | Status Comment
|  | C0004618 | [12 empty] | yes | OPP-006588~07252023~GSA QUOTE.txt | 49 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0004712 | [12 empty] | yes | OPD-014278.txt | 17 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0004736 | [12 empty] | yes | Spec5F349 (exported) - Copy.txt | 79 | 8 |  |  |  | Not Started |  |  |  | Fail | The SIF Import is still running. Please check the quote again later to see if all lines have processed.
|  | C0004766 | [12 empty] | yes | SIF_Tway BOM NM Marines.txt | 5 | 2 |  |  |  | Not Started | [25 empty] | Success
|  | C0004822 | [12 empty] | yes | SIF 2nd Floor File Room 8-8-23.txt | 16 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0004838 | [12 empty] | yes | SIF - 23-1089 - Langlois - Add-on Panel for Front Office - 7-31-23.txt | 1 | 0 |  |  |  | Not Started
|  | C0004729 | [12 empty] | yes | OPP-012877-08032023-AREA 1 WORKSTATIONS - QUOTE.txt | 74 | 29 |  |  |  | Not Started
|  | C0004849 | [12 empty] | yes | view (1).txt | 3 | 0 |  |  |  | Not Started
|  | C0004827 | [12 empty] | yes | OPD-014258- McHenry Co States Attorney Stations (1).txt | 33 | 0 |  |  |  | Not Started
|  | C0004804 | [12 empty] | yes | SIF Austin Water 4th Floor 8-2-23.txt, SIF 4th All ESI and Trendway No Serivces 8-8-23.txt | 133 | 0 |  |  |  | Not Started