## Sheet1
Priority? | RMA? | CPQ Order | concate cpq + vesion | Initial Version Created Date | Latest Version Created Date / Modified Date | Order Submitted Date | Added to ESS Hold Date | Version Hold Status | Reporting Status | IN ESS Hold Queue | Old Order Status | update? | CPQ Status | Most Recent Order Version/ Version in ESS Approval | Is SIF available? | SIF Order File name/s (from CPQ Production) // EDI Purchase Order | Total # of lines | # of SPECIALS lines | In SIF Folder | CPQ Test order # // CPQ Prod Order | Substitute CPQ Test order # | Overall Order Status | AST: WD Code Changes Migrated to ERP Prod? | AST: Code Changes Migrated to CPQ Prod? | Ready to Release/ Submit Order? | SIF File Status: Syteline | Syteline Test notes | SIF File Status: Oracle CPQ | Oracle CPQ Test Notes | SIF File Status: Oracle ERP | Oracle ERP Test Notes | ESS BOM Validation Status | BOM Test Notes What is the error/issue on BOM/Routing? | Next Action **Enter most recent comment on top line in cell** Start With: Initials Date Time (in EST) | Next Action With | JIRA | Resolved? | Resolution | Resolved Date | In ERP Prod Validation Process? Y/N | Date Released to ERP Prod | Date ERP Hold Released | Initials of ESS who Released Hold | Hold Release Comments | week # of when order was submitted by customer | Date released from ESS hold | # of days for BOM Val | Status Comment
|  | C0003710 | [12 empty] | yes | DAVE SIFFFFFF.txt | 4 | 2 |  |  |  | Not Started | [25 empty] | Success
|  | C0003754 | [12 empty] | yes | TLM WEEFOLK CHILDCARE 6-26-23.txt | 6 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0003106 | [12 empty] | yes | 219993_TRENDWAY_SIF_txt_U_of_M_3rd_Fl_CSOM_3-353_219993_061623_REVISED.txt | 9 | 0 |  |  |  | Not Started | [25 empty] | Success
|  | C0005325 | [12 empty] | no | C0005325.txt | 1 | 0 |  |  |  | Not Started
|  | C0004002 | [12 empty] | yes | 763814 C0000405 RMA.txt, 763820 C0000420 RMA.txt | 3 | 1 |  |  |  | Not Started |  |  |  | Fail | File Not Found
|  | C0003662 | [12 empty] | yes | Q149597.txt, Q148596.txt, txt_OPP-012689 R1 order.txt | 76 | 0 |  |  |  | Not Started |  |  |  | Fail | File Not Found
|  | C0003752 | [12 empty] | yes | OPP-006525-06282023-QUOTE.txt | 45 | 22 |  |  |  | Not Started | [25 empty] | Success